## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project | MUST HAVE | no dependency |  | 3- Completed
S1 | S1 | US-001 | work flow , and the milestone 1 objective | MUST HAVE | no dependency |  | 3- Completed
S2 | S2 | US-001 | Data set selction, preprocessing steps , modification and uploading | MUST HAVE | google colab, kaggle |  | 3- Completed
S2 | S2 | US-001 | Presentation regarding the milestone 1 completion | MUST HAVE | powerpoint microsoft |  | 3- Completed
S3 | S3 | US-001 | Work flow and the objective of milestone 2 discussed | MUST HAVE | resources from online |  | 3- Completed
S3 | S3 | US-001 | Milestone 2 - connecting to ml and generation of graph | SHOULD HAVE | Neo4j |  | 3- Completed
S4 | S4 | US-001 | Milestone 3 objective discussed | MUST HAVE | python,sematic |  | 3- Completed
S4 | S4 | US-001 | Milestone 3 enabling the sematic search ,rag pipeline , | SHOULD HAVE | google colab |  | 3- Completed
S5 | S5 | US-001 | Milestone 4 - focusing on the frontend part | MUST HAVE | react |  | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
[8 empty] | 41 | 8 | 6 | 6 | 7 | 8 | 3 | 1 | 0 | 2 | 1
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to project | 2026-02-02 | 2026-02-04 | Sahana | others | 3- completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | work flow , and the milestone 1 objective | 2026-02-05 | 2026-02-07 | Sahana | roadmap | 3- completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Data set selction, preprocessing steps , modification and uploading | 2026-02-07 | 2026-02-11 | Sahana | coding | 3- completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Presentation regarding the milestone 1 completion | 2026-02-12 | 2026-02-13 | sahana,anshu | presentation | 3- completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
US-001 | 5 | Work flow and the objective of milestone 2 discussed | 2026-02-13 | 2026-02-18 | sahana,anshu | roadmap | 3- completed | 5 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
US-001 | 6 | Milestone 2 - connecting to ml and generation of graph | 2026-02-19 | 2026-02-26 | sahana,anshu | coding | 3- completed | 6 | 0 | 1 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Milestone 3 objective discussed (FAISS,Pinecone) | 2026-03-03 | 2026-03-12 | sahana,anshu | roadmap | 3- completed | 9 | 1 | 1 | 1 | 1 | 3 | 2 | 0 | 0 | 0 | 0
US-001 | 8 | Milestone 3 enabling the sematic search ,rag pipeline , | 2026-03-13 | 2026-03-23 | sahana,anshu | coding | 3- completed | 4 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 0
US-001 | 9 | Milestone 4 frontend and creating a running system | 2026-03-25 | 2026-03-29 | sahana | coding(react) | 3-completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
sprint 1 | day 2 | preprocessing steps | conducted a meeting where doubts can be cleared
Sprint | day 4 | milestone 1 outcome | discovered the milestone 1 outcome and conducted the meeting
Sprint | day 11 | milestone 2 overview | conducted meeting regarding the objective of milestone 2 and sharing of works
Sprint | day 17 | milestone 2 outcome | discussed the milestone 2 outcome and clarifies the confusion in all the team members
Sprint | day 25 | milestone 3 objective | listed out the milestone 3 outcomes expected by the guide and the steps to attain the same
Sprint | day 31 | milestone 3 outcome | worked on the presentation and attained the outcome
Sprint | day 40 | milestone 4 | creating a frontend with react native and giving the output of the entire project
Sprint

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | sprint 1 | 2026-02-02 | 2026-02-11 | sahana | reviewing work regularly | theory knowledge | focus on the practical and code part
2 | sprint 3 | 2026-03-03 | 2026-03-19 | anshu | working on the milestone 2 | Delaying review of task | maintaining focus on the coding part
3 | sprint4 | 2026-03-23 | 2026-03-29 | sahana | working on milestone 4 | focusing on formatting | entire focus on the frontend part
4
5
6
7